## Sheet1
Driver Registration Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
View driver registration form	Click add new driver button	View driver registration form	Viewed driver registration form	Google Chrome	Pass	Tested on 02/03/2021
Submit empty driver registration form	Click on submit button	Show error "enter data correctly"	Show error message "enter data correctly"	Google Chrome	Pass	Tested on 02/03/2021
Check for not accepting duplicate email and mobile	Enter duplicate mobile and email	Show error "account exist"	Show message "account exist"	Google Chrome	Pass	Tested on 02/03/2021
Submit form with no images	Enter all data not select any images	Show message select image first	Show message select images first	Google Chrome	Pass	Tested on 02/03/2021
Register driver with correct data and images	Enter driver data with images and click submit button	Create account successfully	Account created successfully	Google Chrome	Pass	Tested on 02/03/2021
Try to create driver account with invalid email address	Enter all driver data correctly but provide invalid email and click submit	Show "error" message invalid email address	Received error message invalid email address	Opera Mini	Pass	Tested on 02/03/2021
Check selection of multiple images in driver registration	Click select images button and try to select multiple images	The admin should be able to select multiple images	Successfully select multiple images	Google Chrome / Opera	Pass	Tested on 02/03/2021
Checking for selection of other file format instead of images	Click select images button and try to select video	Show error message "the file format is not supported	Successfully received error message "file format is not supported"	Google Chrome / Opera	Pass	Tested on 02/03/2021
Enter number instead of letter and letter instead of number	Enter letter in name input filed and letter in mobile input field	The user should be able enter invalid format data	The user not able to enter invalid format data	Google chrome	Pass	Tested on 02/03/2021

Driver Login Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
Checking login form without entering any data and try to submit	Leaved email and password empty and click login button	Login button should not work and show error message	Login button not working and receive error message	Android X	Pass	Tested on 06/03/2021
Enter invalid email and password and try to login in the app	Enter invalid email and password	Should give invalid email or password error message	Successfully received error message	Android X	Pass	Tested on 06/03/2021
Enter correct email but wrong password and try to login	Email – basitdak@gmail.com Password- 123456	the user should receive invalid password message	Received invalid password error message	Android X	Pass	Tested on 06/03/2021
Enter invalid email and valid password	Email – basi@gmali.com Password- 1234	The user should receive error message	Received error message "account does not exist	Android 9.0	Pass	Tested on 06/03/2021
Enter correct email and password and try to login in the system	Email- basitdak@gmail.com Password- 1234	Should successful login	Successfully login in the system	Android X	Pass	Tested on 06/03/2021
After login user should be directed to main activity	Click login button	User should be able to view main screen	Successfully view home screen	Android X	Pass	Tested on 06/03/2021
Try to check forgot password option functionality	Click forgot password button	Should to directed to forgot password screen	Successfully directed to forgot password activity	Android X	Pass	Tested on 06/03/2021
Enter invalid email address in the forgot password	Email- basi@gmail.com	The user should receive error message	Successfully received error message account does not exist	Android X	Pass	Tested on 06/03/2021
Enter correct email address and check for forgot password functionality	Email- basitdak@gmail.com	Request should be send to server and user should receive success message	Request successfully send and user received message	Android X	Pass	Tested on 06/03/2021
After successfully request send to server check that user receive email with pin code	Click forgot password button	User should receive email	User successfully received email with pin code	Android X	Pass	Tested on 06/03/2021

Driver Current Location Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
Lunch application	Click application icon	The should view Google map on the lunch of main activity	Successfully view Google map	Android X	Pass	Tested on 10/03/2021
Show or set cursor on user current location	Lunch app	Show user current location	Show user current location	Android 8.0	Pass	Tested on 10/03/2021
Update user current location every second	None	Location should be update	Location updated every second	Android 8.0	Pass	Tested on 10/03/2021
Checking user location when user device have no internet connection	None	The system use GPS in case no connection	Successfully used GPS	Android 8.0	Pass	Tested on 10/03/2021
Check location is working when location services is disable	Lunch app main activity and disable location service	The should receive error message and app crash	Received error message and app crashed	Android 8.0	Pass	Tested on 10/03/2021
The app should ask for location permission in the start of main activity	Lunch main activity	Show the location permission dialog	Successfully show location permission dialog	Android 8.0	Pass	Tested on 10/03/2021
Disable internet and run app to check for user current location	Disable internet connection	The user should receive error message	User received no internet error message	Android 8.0	Pass	Tested on 10/03/2021
Current location cursor should change with location change	Change device location	The cursor should change	Cursor changing successfully	Android 8.0	Pass	Tested on 10/03/2021

User Module Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
View profile	Click profile button	Should open profile activity and display driver information	Successfully opened and display customer information	Android X	Pass	Tested on 13/03/2021
The driver change information and try update	Change data and click update	Successfully change information	Successfully change information	Android X	Pass	Tested on 13/03/2021
Open support activity	Click support button	Display support activity and submit customer query	Successfully display and submit customer query	Android X	Pass	Tested on 13/03/2021

Campaign Module Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
Driver receive campaign request from user app	Run app	Should receive campaign request	Successfully received campaign request	Android 7	Pass	Tested on 15/03/2021
Driver close and try to receive campaign request from user	Close app	Should able to received campaign request	Successfully received campaign request	Android 8	Pass	Tested on 15/03/2021
Try to receive campaign request without completing trail	Run app	The driver should not receive campaign request without trail completion	Driver not received any campaign request from user	Android X	Pass	Tested on 15/03/2021
Receive campaign request	None	Ring tone should be play when request receive	Ringtone play successful on received of request	Android X	Pass	Tested on 15/03/2021
Driver view campaign and try to reject it	Click reject button	Request should be rejected and driver will return to main screen	Successfully reject request and redirected to main screen	Android 9.0	Pass	Tested on 15/03/2021
Driver accept campaign request	Click accept button	Should be redirected to reach installation center screen	Successfully redirected to installation center screen	Android X	Pass	Tested on 15/03/2021
Driver redirected to installation center activity	Start campaign	Route should be created to installation center	Route created successfully to installation center	Android X	Pass	Tested on 15/03/2021
Driver complete installation	Click complete installation button	Should be redirected to upload images screen	Successfully redirected to upload images screen	Android X	Pass	Tested on 15/03/2021
Driver select and upload multiple images for user to view	Click select and upload button	Should be able to select and upload multiple images	Successfully select and upload multiple images	Android 9	Pass	Tested on 15/03/2021
On successfully uploading to images driver should start show ads on car	Click start button	Should be redirected to campaign main screen	Successfully redirected	Android 8	Pass	Tested on 15/03/2021
Start showing ads	Open main screen	App should track and store driver data	Successfully tracking and storing data	Android X	Pass	Tested on 15/03/2021
On completion of campaign driver should be redirected to home screen	None	Driver should be redirected to main and campaign amount should be transfer to driver account	Successfully redirected to main and amount transfer successfully into user account	Android X	Pass	Tested on 15/03/2021

Driver Trail Module Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
Start driver tail	Click start tail button	Successfully start trail	Successfully start tail	Android X	Pass	Tested on 17/03/2021
Tracking driver trail and store in database	Running application	Successfully tracking driver	Successfully tracking driver	Android X	Pass	Tested on 17/03/2021
Atomically checking for completion of driver trail	Running application	Successfully checking	Successfully checking	Android X	Pass	Tested on 17/03/2021
Updating driver trail location every minute	Running application	Updating location	Updating location successfully	Android X	Pass	Tested on 17/03/2021
Disable internet connection and tracking trail	Running application	Display error message	Successfully display error message	Android X	Pass	Tested on 17/03/2021
Disable location services in continuous driver tracking	Click disable location service	Display alert message	Successfully display alert message	Android X	Pass	Tested on 17/03/2021
Redirect driver to campaign request home page	Auto complete driver trail	Should redirect driver to request page	Successfully redirect driver	Android X	Pass	Tested on 17/03/2021

Admin Account Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
Enter invalid username and password	Username: basie	Should display error message	Successfully display error message	Chrome/Opera	Pass	Tested on 19/03/2021
	Password: 12345
Enter empty password and username	Username: ""	Should display error message fill value correctly	Successfully display error message	Chrome/Opera	Pass	Tested on 19/03/2021
	Password: ""
Enter correct username and password	Username: basit	Redirected admin to dashboard	Successfully redirected to dashboard	Chrome/Opera	Pass	Tested on 19/03/2021
	Password: 12345
Enter correct password and incorrect username	Username: erkl	Display error message	Successfully display error message	Chrome/Opera	Pass	Tested on 19/03/2021
	Password: 12345
Enter incorrect password and valid username	Username: basit	Display error message	Successfully error message	Chrome/Opera	Pass	Tested on 19/03/2021
	Password:12345
Login form should have forgot password option	Click forgot password button	User should be redirected to forgot password form	Successfully redirected	Chrome/Opera	Pass	Tested on 19/03/2021
Enter invalid email address in the forgot password	Email: basit@gmail.com	Should display error message invalid email message	Successfully display error message	Chrome/Opera	Pass	Tested on 19/03/2021
Enter correct email address	Email: tcomporog@gmail.com	Admin should be redirected to new password page	Successfully redirected to new password form	Chrome/Opera	Pass	Tested on 19/03/2021
Enter different for both input field in new password form	Password 1: 1234	Should display error message "password does not match"	Successfully display error message "password does not match"	Chrome/Opera	Pass	Tested on 19/03/2021
	Password 2: 12345
Enter both same password in the enter new password form	Password 1: 12345	Should change password in the database	Successfully changed password in the database	Chrome/Opera	Pass	Tested on 19/03/2021
	Password 2: 12345
View the update admin page	Click on update admin	Redirected to admin update form	Successfully redirected	Chrome/Opera	Pass	Tested on 19/03/2021
Change admin information in the update page and try to save	Name: Abdul Basit	Update and save new information	Successfully save and store information	Chrome/Opera	Pass	Tested on 19/03/2021
	Email: tcomprog@gmail.com
	Password: 1234
Open add new admin page	Click add new admin button	Redirect to add admin form	Successfully redirected	Chrome/Opera	Pass	Tested on 19/03/2021
Submit form with no values in the add admin	None	Display error message	Successfully display error message	Chrome/Opera	Pass	Tested on 19/03/2021
Enter invalid email address	Email: Tcmom.com	Display error message "invalid email"	Successfully display error message	Chrome/Opera	Pass	Tested on 19/03/2021
Enter all record correctly without selecting images	Name: Abdul Basit	Display error message "select images first"	Successfully display error message	Chrome/Opera	Pass	Tested on 19/03/2021
	Email: tcomprog@gmail.com
	Address: Peshawar
	Password: 1234
	Level: super
Enter all data correctly and select image	Name: Abdul Basit	Create new admin account	Successfully created admin account	Chrome/Opera	Pass	Tested on 19/03/2021
	Email: tcomprog@gmail.com
	Address: Peshawar
	Password: 1234
	Level: super
	Image: select
Try to select multiple images in creating admin account	Click select button and press Art + A	Admin should not be able to select multiple images	Admin not able to select multiple images	Chrome/Opera	Pass	Tested on 19/03/2021
View admin list	Click button admin list	Display admin list	Successfully display admin list	Chrome/Opera	Pass	Tested on 13/02/2021
Try to delete admin account	Click delete button	Should delete admin account	Successfully deleted admin account	Chrome/Opera	Pass	Tested on 19/03/2021
Admin click sign-out	Click sign-out button	Should sign-out	Successfully sign-out	Chrome/Opera	Pass	Tested on 19/03/2021
Admin leave account for 30 minute without performing any activity	None	Account should be sign Out automatically	Successfully sign-out	Chrome/Opera	Pass	Tested on 19/03/2021

Driver List Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
View driver list	Click view driver list	Display driver list	Successfully display driver list	Chrome	Pass	Tested on 21/03/2021
Click edit driver profile and try to update driver information	Click edit button	Display driver profile	Successfully display driver profile	Chrome	Pass	Tested on 21/03/2021
Click update driver info	Click profile button	Display form with driver old information	Successfully display	Chrome	Pass	Tested on 21/03/2021
Change driver information and click update	Name: Abdullah Khan	Update and store driver new information	Successfully update and store driver information	Chrome	Pass	Tested on 21/03/2021
	Password:1234
Click change driver account balance and update	Balance: 0	Update driver account balance	Successfully update account balance	Chrome	Pass	Tested on 21/03/2021
Click block driver account	Click block button	Account block and sing out	Driver blocked and sign-out	Chrome	Pass	Tested on 21/03/2021
View driver history and record	Click record button	Display driver history	Successfully display driver history	Chrome	Pass	Tested on 21/03/2021

Admin Campaign Module Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
View active campaign	None	Display active campaign	Display active campaign	Edge-11	Pass	Tested on 23/03/2021
Edit active campaign	None	Display campaign profile	Successfully display campaign profile	Edge-11	Pass	Tested on 23/03/2021
Assign new driver to active campaign	Click assign driver button	Generate new campaign request	Successfully generate campaign request	Edge-11	Pass	Tested on 23/03/2021
Delete driver from active campaign	Click delete button	Delete driver from active campaign	Successfully delete driver from active campaign	Edge-11	Pass	Tested on 23/03/2021
Assign new driver to pending campaign after 12 hours	Click assign new driver button	Generate new campaign request	Successfully generate campaign request	Edge-11	Pass	Tested on 23/03/2021
View pending campaign list	Click pending campaign button	Display pending campaign list	Successfully display pending campaign list	Edge-11	Pass	Tested on 23/03/2021

User Account Module Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
Enter invalid mobile number for user registration	Mobile: 2383839483	OTP will not send it and give error message	OTP is not send it and give error message	Android X	Pass	Tested on 25/03/2021
Submit empty user registration activity	Mobile: ""	Display error message	Successfully display error message	Android X	Pass	Tested on 25/03/2021
	Email: ""
	Password: ""
	Image: none
	Address: none
Fill correct information and select image to register new user	Mobile: 03059235079	Create new user account	Successfully create new user account	Android X	Pass	Tested on 25/03/2021
	Password: 12345
	Address: Peshawar
	Email: tcomprog@gmail.com
Enter invalid mobile and password in user login	Mobile: 230983409834	Display error message invalid phone or password	Successfully display error message	Android X	Pass	Tested on 25/03/2021
	Password: 23423
Enter valid mobile and invalid password	Mobile: 03059235079	Display error message "invalid password:	Display error message	Android X	Pass	Tested on 25/03/2021
	Password:123
Login with correct mobile and password	Mobile: 03059235079	Login user	Successfully login user	Android X	Pass	Tested on 25/03/2021
	Password:12345
Click keep me login option	Click keep me login checkbox	Keep user login for later	Keep user login for later user	Android X	Pass	Tested on 25/03/2021
Try to forgot password with a correct email address	Email: tcomprog@gmail.com	Change user password	Change user password	Android X	Pass	Tested on 25/03/2021

User Campaign Module Testing
Action	Inputs	Expected Output	Actual Output	Test Platform	Test Result	Test Comment
Click create new campaign	Click campaign button	Redirect to create campaign page	Redirected to create campaign activity	Android 9.0	Pass	Tested on 27/03/2021
Check user balance before moving to campaign details page	Click move to details	Check If the user have enough balance redirect else show alert message	Successfully show alert message	Android 9	Pass	Tested on 27/03/2021
Try to submit create campaign form with empty information	numberofCar:	Display error message fill form correctly	Display error message	Android 9.0	Pass	Tested on 27/03/2021
	TotalKm:
Select multiple image in the campaign creation	Select multiple images	Allow to select multiple images	Allow user to select multiple images	Android 9.0	Pass	Tested on 27/03/2021
Enter correct coupon code to get discount	Code: 10xke	Give discount to user	Give discount	Android 9.0	Pass	Tested on 27/03/2021

Integration Test Case
Test Case ID	Objective	Description	Expected Output
IT-TC-1	Check interface between User app registration and Firebase module	Enter mobile number and click send button and send mobile to Firebase module	Send OTP to user mobile and return OTP to registration module
IT-TC-2	Check interface between User app Login and server module	Enter mobile number and password and click login button	Send user data to server and return JSON Object to Login module
IT-TC-3	Check interface between User app registration and Server Module	Enter mobile number, name, address, age, city, cnic, email and select image and click register button	Received all data from registration module and send it to server and return JSON Object to registration module
IT-TC-4	Check interface between User app Main and Location Module	Start running app main module send request to return user current location	Start tracking user location and ask for permission from user and return user current location in form of array
IT-TC-5	Check interface between User app Login and Data storage module	Click button keep me login and send user details in form of array	Data storage module receive user information and store it for long time and return true to the Login module
IT-TC-6	Check interface between User app Server and Campaign module	Enter button to create campaign with entering different information and selecting multiple images from user mobile	Received all information related to campaign and perform validate on campaign if information is correct send the data to the server for creating new campaign and return details in the form of Json array
IT-TC-7	Check interface between User app Main and Fragment module	Click button to view campaigns and send number of fragment with title to create view for the user	Create fragment according to data send by main module and display information on each view
IT-TC-8	Check interface between User app Main and Adapter module	Click button to view list of campaign and send number of card to be create send data along with each card such title, id, description, images, date	Received data and send data to each view holder and view and return view holder to main module to display information
IT-TC-9	Check interface between User app Main and Config module	Main module call conifig module in the start of application to check for network connectivity	Receive request and check for network connectivity and return if true is device have connectivity and false if the device not have any network connectivity
IT-TC-10	Check interface between User app Main and Services module	Check interface between User app Main and Services module	Download and return image
IT-TC-11	Check interface between Driver app Login and Server module	Enter mobile and password and click login button and send data to Server module	Send request to service and verify driver data and return Json Array in response to Login module
IT-TC-12	Check interface between Driver app Login and Network module	On start of login module a request is to Network module to check for new connectivity	Check for connectivity and return result to Login module
IT-TC-13	Check interface between Driver app Driver and Configure module	Driver module sending request access all constant in the app and in the request the constant name is send to Configure module	Receive constant name and return value of the constant in result
IT-TC-14	Check interface between Driver app Driver and Data Constrainer module	Enter button keep me login and send data in the form of array	Store the user information and also store the state of user account
IT-TC-15	Check interface between Driver app Driver and Server module	Driver send request along with data and type of request	Received data and request type and send request server and return response to the module
IT-TC-16	Check interface between Driver app Driver and Adapter module	Click button to view list of campaign and send number of card to be create send data along with each card such title, id, description, images, date	Received data and send data to each view holder and view and return view holder to main module to display information
IT-TC-17	Check interface between Driver app Driver and Background Service module	Driver module send request to background service module to start tracking of driver data in background and start service in android app	Received service and starting tracking and sending information to server
IT-TC-18	Check interface between Driver app Driver and SQLITE module	Enter button to save user tracking details such name, id, kms, status	Save all data in SQLite database and return response
IT-TC-19	Check interface between Driver app Driver and Presences module	Enter save button to save user activities history in the local phone and then upload to server	Save the history in local phone storage and start uploading to server and return response
IT-TC-20	Check interface between Driver app Driver and Images module	Send image URL to download, store and load image in user phone	Received image url and send request server for downloading image and return image in the form of Bitmap
IT-TC-21	Check interface between Admin web app Admin and Connect module	Send request to make connectivity with the database	Make connection with data and return connection object
IT-TC-22	Check interface between Admin web app Client and Connect module	Send request to make connectivity with the database	Make connection with data and return connection object
IT-TC-23	Check interface between Admin web app Admin and Include module	Sending request with extra information to get file content of different files	Received request and return content according to the request data
IT-TC-24	Check interface between Admin web app Admin and API module	Admin module send request to get data from data without loading the page and parameter	Received parameter get data from database and return it to the Admin module in the form Json array
IT-TC-25	Check interface between Admin web app Admin and Driver module	Click register new driver button enter information for driver and select images	Insert driver data in database and upload images to server return response message
IT-TC-26	Check interface between Admin web app Admin and User module	Sending request to user list and user content	Get user data from database and return in JSON array format
IT-TC-27	Check interface between Admin web app Admin and Email module	Enter email address and send email address to Email module	Received email address and send email to the received email address
IT-TC-28	Check interface between Admin web app Admin and Jazz cash module	Enter driver Jazz cash mobile number and try to sending money to driver	Send money to driver and return response and save data into the database
IT-TC-29	Check interface between Admin web app Admin and FCM module	Enter user mobile id click send button	Received FCM id and send dynamic notification to user
IT-TC-30	Check interface between Admin web app Admin and Images module	Sending image address to images module	Return image in response
IT-TC-31	Check interface between Admin web app Admin and plugins module	Send request for plugins	Return plugin in response
IT-TC-32	Check interface between Admin web app Admin and Videos module	Sending video url	Return video in response to module which send the request
IT-TC-33	Check interface between Admin web app Admin and Tracking module	Enter or search user id or mobile number and click track button	Received data and get user location from database and return it to the specific module